## Risk Watch List
Risk # | Buiness Area | Description (Defined Risk) | Business Impact | Likeli-hood | Severity | Level of Control | Significance (Likelihood + Severity+ Level of Control) | Risk Strategy | Risk Mitigation Plan
1 | AWS EC2 | If US West (Portland/Phoenix), US East (Atlanta/Tampa), and GovCloud (DC) fail, entire cloud infrastructure will be down for US. If just one or two fails, services can shift to another AWS site with heavier load. | Atlanta/DC hot sites may not compensate. If only single, shift over to another location. II CaaS will remain for 911 support. Any serious community wide or larger threats will be an issue. | 1 | 5 | 3 | 9 | Transfer (1 or 2 fail) / Control (all fail) | Maintain hot sites at DC / Atlanta sites and one emergent cluster at Phoenix site
2 | AWS S3 | If redundancy fails and data becomes corrupt, may lose records and any potential progress made. | ESS wouldn't be viewed as reliable anymore and may cause serious issues since S3 would be used for Pentagon and CDC. | 3 | 5 | 1 | 9 | Transfer | Repeat - maintain hot sites at DC / Atlanta, which are the 2 of 5 sites that will use S3
3 | AWS RDS | If RDS fails at Phoenix site, redundancy and non-S3 data storage will fail at Portland / Tampa sites. At Portland/Tampa sites fail, automatic failover will commence at Phoenix site without issue. | Storage maintenance, geographical redundancy, and database access would be temporarily hindered if Portland/Tampa or permenantly if Phoenix. | 1 | 3 | 2 | 6 | Assumption | Additional RDS services would other CSPs could be used. For cost efficiency, ignore until fails.
4 | AWS CloudFront | If CloudFront fails, main service for content delivery would be unusable. | Content delivery would have temporary performance issues until picked up automatically with EC2 and S3. | 1 | 1 | 2 | 4 | Transfer | Since CF is used as ESS news, utter failure could still be managable by relying on actual news networks
5 | AWS Direct Connect | If Direct Connect fails, private two-way communication via cloud between DC and Atlanta would be down. | DC/Atlanta would have to rely on open communication that could be secured with extra effort or hard lines that two would have to be maintained and secured. | 2 | 3 | 1 | 6 | Transfer | Back-up VPC with VPN tunneling and heavily sheathed and hidden hardlines would be best. A contingency with a contingency.
6 | II CaaS / PureCloud | If II CaaS fails, national communications would be down completely. Any national issues wouldn't be reportable. | ESS wouldn't be able to function at all. Dependency on local hardlines would do too little. | 1 | 5 | 5 | 11 | Avoidance | Provide II any emergent equipment to ensure no failure occurs.

## Legend
Key | Risk Significance
Likelihood
| 1 | Very unlikely
| 2 | Somewhat unlikely
| 3 | 50/50 Chance
| 4 | Highly likely
| 5 | Nearly Certain
Severity
| 1 | Minor impact on cost, schedule, performance, etc.
| 2 | Moderate impact on cost, schedule, performance, etc.
| 3 | Significant impact on project baselines
| 4 | Very significant impact on project baselines
| 5 | Disastrous impact, probable project failure
Level of Control
| 1 | Essentially avoidable through selected risk mitigation actions
| 2 | Highly controllable through organization or project actions
| 3 | Moderately controllable through organization or project actions
| 4 | Largely uncontrollable by the organization or project actions
| 5 | Uncontrollable by the organization or the project
Risk Strategies
| 1 | Assumption - accepting the risk and its impact should it occur, best suited for low risk classifications
| 2 | Avoidance - Not willing to accept the risk. This generally involves eliminating the source of the risk by a change in concept, requirements, specification and/or practices to reduce the risk to an acceptable level
| 3 | Control - This option does not attempt to eliminate the source of the risk but seeks to reduce or mitigate the effect should the risk occur. It manages the effects of risk in a manner that reduces the likelihood and/or consequences of its occurrence on the project.
| 4 | Transfer - This option may reallocate risk from one part of the system or organization to another thereby reducing the overall risks probability of occurrence and impact.